## Sheet1 (2)
Activity | Detail Activity | Start Time | Days To Complete
Data Gathering | Obtain necessary permissions | 2019-04-23 | 2
| Obtain dataset | 2019-04-25 | 1
Full I/O design | Design all the UI classes with respect to class diagram | 2019-04-25 | 10
| Implement all controller classes using class diagram | 2019-04-25 | 15
Login Subsystem Implementation | Implement Login Authentication Subsystem | 2019-04-25 | 1
Database design | Table creations according to ERD |  | 1
| Connection to database and testing with test data | 2019-04-26 | 1
2019-05-01
General Facilities Subsytem Implementation | Implement General Facilities Subsystem | 2019-04-27 | 2
| Retreiving test data and testing the UI window | 2019-04-29 | 1
| Testing manually with ping or tracert against our subsystem | 2019-04-29 | 2
DNS Filtering Subsystem testing | Testing with new datasets | 2019-05-01 | 5
| Trying new approaches without proxy server | 2019-05-06 | 7
2019-05-07
HTTP Filtering Check Subsystem Implementation | Implement HTTP Filtering Check Subsystem | 2019-05-13 | 10
HTTP Filtering Check Subsystem Unit Testing | Testing content using manual approach | 2019-05-23 | 5
| Testing content using other proxy servers | 2019-05-28 | 5
| UI testing for new datasets | 2019-06-02 | 3
2019-05-14
TCP Filtering Check Subsystem Implementation | Implement HTTP Filtering Check Subsystem | 2019-05-13 | 8
TCP Filtering Check Subsystem Unit Testing | Testing for various known datasets | 2019-05-21 | 5
2019-05-20
Censorship Tracking Subsystem Implementation | Implement Censorship tracking subsystem | 2019-06-02 | 5
Integration of system modules | Integration of all subsystems | 2019-06-07 | 4
Database Testing | Database testing for old data sets | 2019-06-11 | 5
| Database testing for old data sets | 2019-06-16 | 5
Integration testing | Integration testing | 2019-06-21 | 10
Beta Testing | Beta Testing | 2019-07-01 | 4
Necessary modifications | Make necessary modifications | 2019-06-07 | 32

## Sheet1
15/6/2020
15/6/2020
Activity | Detail Activity | Start Time | Days To Complete | 19/6/2020
Initial requirements analysis | Feasibility analysis | 15/6/2020 | 5 | 19/6/2020
| Design documentation | 2020-12-07 | 3 | 24/6/2020
| Entity Relationship Diagram |  | 3 | 24/6/2020
| UML Class Diagrams | 2020-10-09 | 4 | 24/6/2020
| Dataflow Diagrams | 2020-10-15 | 3 | 24/6/2020
2020-10-15
Modules design (UI/UX) | Doctor-Authentication SignUp & Login UI/UX design | 2020-10-12 | 3
| Client SignUp & Login UI/UX design | 2020-10-13 | 5
2020-10-14
| Doctor-Authentication Certificate Verification UI/UX design | 2020-10-15 | 3
| Doctor-Information Enter & Update information UI/UX design | 2020-10-16 | 2
| Doctor Listing UI/UX design | 2020-10-17 | 4
| Client Enter & Update information UI/UX design | 2020-10-18 | 2
Development of certain sub-modules | Development of Doctor and Client SignUp & Login | 2020-01-07 | 4
Remaining modules design (UI/UX) | Design of Doctor-Client Appointment sub-module UI/UX | 2020-01-07 | 7
Design of Doctor-Client Payment sub-module UI/UX | Mobile & Online payment design | 2020-05-07 | 5
| Transactional Transparency Management design | 2020-05-07 | 4
| Revenue Management design | 2020-05-07 | 5
Development of other sub-modules & design contd | Doctor-Information sub-module development | 2020-10-07 | 10
| Doctor-Authentication sub-module development | 2020-10-07 | 7
| Client module development | 2020-10-07 | 15
Testing | Unit testing on Doctor-Information sub-module | 20/7/2020 | 3
| Unit testing on Doctor-Authentication sub-module | 17/7/2020 | 3
| Integration testing on Doctor module | 23/7/2020 | 5
| Integration testing on Client module | 25/7/2020 | 5
Development of other modules & design contd | Design of Doctor-Client Session-Management module | 2020-01-08 | 7
| Design of Doctor-Client Feedback module | 2020-01-08 | 5
| Development of Doctor-Client Appointment module | 2020-08-08 | 5
| Development of Doctor-Client Payment module | 2020-08-08 | 17
| Development of Doctor-Client Session Management module | 13/8/2020 | 15
| Development of Doctor-Client Feedback module | 13/8/2020 | 10
Testing | Unit testing on Doctor-Client Appointment module | 13/8/2020 | 3
| Unit testing on Doctor-Client Feedback module | 23/8/2020 | 3
| Unit testing on Doctor-Client Payment module | 25/8/2020 | 3
| Unit testing on Doctor-Client Session Management module | 28/8/2020 | 3
| Regression testing | 2020-01-09 | 5
| Integration testing on whole Doctor-Client module | 2020-06-09 | 15
| Whole system testing | 22/9/2020 | 10
| Server deployment | 2020-05-10

## Sheet2
Activity Summary | Activity ID | Activity Details | Start Time | Duration
Initial requirements analysis | 1 | Feasibility analysis | 2020-06-10 | 5
| 2 | Design documentation | 2020-06-10 | 3
| 3 | Entity Relationship Diagram | 2020-06-12 | 3
| 4 | UML Class Diagrams | 2020-06-15 | 4
| 5 | Dataflow Diagrams | 2020-06-15 | 3
Modules design (UI/UX) | 6 | Doctor-Authentication SignUp & Login UI/UX design | 2020-06-19 | 3
| 7 | Client SignUp & Login UI/UX design | 2020-06-19 | 5
| 8 | Doctor-Authentication Certificate Verification UI/UX design | 2020-06-24 | 3
| 9 | Doctor-Information Enter & Update information UI/UX design | 2020-06-24 | 2
| 10 | Doctor Listing UI/UX design | 2020-06-24 | 4
| 11 | Client Enter & Update information UI/UX design | 2020-06-24 | 2
Development of certain sub-modules | 12 | Development of Doctor and Client SignUp & Login | 2020-06-28 | 7
Remaining modules design (UI/UX) | 13 | Design of Doctor-Client Appointment sub-module UI/UX | 2020-06-28 | 7
Design of Doctor-Client Payment sub-module UI/UX | 14 | Mobile & Online payment design | 2020-07-05 | 5
| 15 | Transactional Transparency Management design | 2020-07-05 | 4
| 16 | Revenue Management design | 2020-07-05 | 5
Development of other sub-modules & design contd | 17 | Doctor-Information sub-module development | 2020-07-10 | 10
| 18 | Doctor-Authentication sub-module development | 2020-07-10 | 7
| 19 | Client module development | 2020-07-10 | 15
Testing | 20 | Unit testing on Doctor-Information sub-module | 2020-07-20 | 3
| 21 | Unit testing on Doctor-Authentication sub-module | 2020-07-17 | 3
| 22 | Integration testing on Doctor module | 2020-07-23 | 9
| 23 | Integration testing on Client module | 2020-07-25 | 7
Development of other modules & design contd | 24 | Design of Doctor-Client Session-Management module | 2020-08-01 | 7
| 25 | Design of Doctor-Client Feedback module | 2020-08-01 | 7
| 26 | Development of Doctor-Client Appointment module | 2020-08-08 | 5
| 27 | Development of Doctor-Client Payment module | 2020-08-08 | 17
| 28 | Development of Doctor-Client Session Management module | 2020-08-13 | 15
| 29 | Development of Doctor-Client Feedback module | 2020-08-13 | 10
Testing | 30 | Unit testing on Doctor-Client Appointment module | 2020-08-13 | 3
| 31 | Unit testing on Doctor-Client Feedback module | 2020-08-23 | 3
| 32 | Unit testing on Doctor-Client Payment module | 2020-08-25 | 3
| 33 | Unit testing on Doctor-Client Session Management module | 2020-08-28 | 3
| 34 | Regression testing | 2020-08-31 | 6
| 35 | Integration testing on whole Doctor-Client module | 2020-09-06 | 15
| 36 | Beta testing | 2020-09-21 | 9
Server deployment